## Portfolio
Project Performance Monitoring System Portfolio
13 April 2026
No. | Country | Loan / Grant No. | Project Number | Project Officer | Project Analyst | Project Name | Executing Agency | Last Updated | I. Basic Data | [14 empty] | II. Project Performance Rating | [11 empty] | III. Implementation Status | [33 empty] | IV. Financial Management |  |  |  |  | V. Output |  |  |  | VI. Safeguards
[9 empty] | Approval | Signing | Effective | Original Closing | Revised Closing | Financial Closing | PCR Due Date | Original Amount | Net Effective | Allocated | Unallocated | Committed | Uncommitted | Disbursed | Undisbursed | Output |  | Contract Award |  | Disbursement |  | Financial Management |  | Safeguards |  | Overall |  | Contract Award (eOps Target) | [5 empty] | Contract Award (Achievable Estimate) |  |  |  |  | Contract Award (Actual) | [5 empty] | Disbursement (eOps Target) | [5 empty] | Disbursement (Achievable Estimate) |  |  |  |  | Disbursement (Actual) | [6 empty] | Rating | [5 empty] | Score | Rating | Indicators | [7 empty] | Rating
[10 empty] | Signing | Effective | Original Closing | Revised Closing | Financial Closing | PCR Due Date | Original Amount | Net Effective | [6 empty] | Current | Yearend | Current | Yearend | Current | Yearend | Current | Yearend | Current | Yearend | Current | Yearend | 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | 2026 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | 2026 | 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | 2026 | 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | 2026 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | 2026 | 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | 2026 |  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8

## <Approval numbers>
Project Performance Monitoring Sheet
Update as of
| Project Name: | [6 empty] | Sector/Subsector:
| Project Number | [6 empty] | Project Officer:
| Loan/Grant Number: | [6 empty] | Project Analyst:
| Executing/Implementing Agency: | [6 empty] | Project Document Link:
| ADB Administering Unit: |  |  | If TRJM, date of project transfer: |  |  |  | Project Handover Document Link:
~ | A. Loan/Grant Basic Data
~ | ADB Financing | Government Financing | Total ($ million equivalent) |  | PCR Due Date |  | Environment Category | Involuntary Resettlement Category | Indigenous People's Category | Gender Category
~
~ | Product | Source | Approval | Signing | Effectivity | Closing |  | % Elapsed Time | Financial Closing | Amount | [13 empty] | Remarks
~ | [5 empty] | Original | Revised |  |  | Original | Net Effective | Allocated |  | Unallocated |  | Committed |  | Uncommitted |  | Disbursed |  | Undisbursed
[9 empty] | - |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
[9 empty] | - |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
[9 empty] | - |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
[9 empty] | - |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
~ | [8 empty] | Total | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
~ | B. Project Rating
~ | Operation Project Rating
~ | Parameters | Outputs | Contract Awards (%) | Disbursement (%) | Financial Management | Safeguards | Overall Rating
| Ratings |  | 0% | 0%
Reason (if FA or AR)
~
~ | Consecutive Overall Project Rating
~ | Validated |  |  |  | Current
~ | 2024, Q4 | 2025, Q1 | 2025, Q2 | 2025, Q3 | 2025, Q4
~
~ | C. Contract Awards and Disbursements
~ | CA | Total Cumulative | Q1 2025 |  | Q2 2025 |  | Q3 2025 |  | Q4 2025 |  | 2025 Total
~ |  |  | eOps | Committed | eOps | Committed | eOps | Committed | eOps | Committed | eOps | Committed
Target
Achievement
| (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
~ | DB | Total Cumulative | Q1 2025 |  | Q2 2025 |  | Q3 2025 |  | Q4 2025 |  | 2025 Total
~ |  |  | eOps | Committed | eOps | Committed | eOps | Committed | eOps | Committed | eOps | Committed
Target
Achievement
| (%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
~
~ | D. Contract Awards and Disbursements (Annual Target vs. Actual CAD and CAD Ratios)
~ | Net Amt. | Uncontr. | Projn | Target CAR | YTD Projn | Achvd | Achvd % | YTD Achvd | Achvd | YTD Trgt | Undisb. | Projn | Target DR | YTD | Achvd | Achvd % | YTD Achvd | Achvd DR | YTD Trgt
~ |  | Amt.(A) | (B) | (D) = B/A a,b | (E) | (F) | (G) = F/B | % (H)=F/E | CAR % a,b | % CAR a,b | Amt. (A) | (B) | (D)=B/A b,c | Projn | (F) | (G)=F/B | % (H)=F/E | % b,c | % DR b,c
~ | [13 empty] | (E)
|  |  |  | 0% |  |  | 0% | 0% |  |  |  |  | 0% |  |  | 0% | 0% | 0% | 0%
~
~ | E. Output Delivery and Procurement
Note: If procurement is still in process, please indicate status of procurement processing in the status.
~ | Output 1: Climate-resilient water supply and sanitation infrastructure rehabilitated and expanded
~ | Package No. (as in Proc. Plan) | Description |  | Contractor | Contract No. (PCSS) | Contract Amount ($ equiv.) | Disbursement ($ equiv.) | Contract Completion Date | Status | Contract Progress |  | Status/Progress of Output Delivery
| Total |  |  |  |  | 0 | 0
~
~ | Output 2: Sustainable business model and institutional capacity developed
~ | Package No. (as in Proc. Plan) | Description |  | Contractor | Contract No. (PCSS) | Contract Amount ($ equiv.) | Disbursement ($ equiv.) | Contract Completion Date | Status | Contract Progress |  | Status/Progress of Output Delivery
~
~ | Project Management
~ | Package No. (as in Proc. Plan) | Description |  | Contractor | Contract No. (PCSS) | Contract Amount ($ equiv.) | Disbursement ($ equiv.) | Contract Completion Date | Status | Implementation Status
Total
Advance Account
Grand Total
~
~ | F. Financial Management Compliance
~ | APFS | FY2018 | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | Remarks
Timeliness (date submitted)
Quality (date accepted by ADB)
Disclosure (date)
~ | AEFS | FY2018 | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | Remarks
Timeliness (date submitted)
Quality (date accepted by ADB)
Disclosure (date)
~
~ | G. Environmental Safeguards Compliance (fill in as applicable)
~ |  | IEE | EIA | Semi-annual report (currently due) | Grievance Redress Mechanism | Corrective Action Plan (CAP) - Current | Status of CAP
~
~ | H. Social Safeguards Compliance (fill in as applicable)
~ |  | LARP | Due Diligence Report | Semi-annual report (currently due) | Grievance Redress Mechanism | Corrective Action Plan (CAP) - Current | Status of CAP
~
~ | I. Contracts (including any IDC)
~ | Loan / Grant | Contract | Description |  | Procurement/ Selection Method | Contract Type | Contractor |  | Contract Estimate | Contract Amount | Disbursed Amount | Disbursed vs Contract | Contract Status | Related Output Indicator | Status of Implementation / Procurement |  |  |  | COMMITTED | ALLOCATED
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0
| DO NOT INSERT BELOW THIS ROW | [17 empty] | 0
|  | FY2023: Total; FY2025: 0; FY2026: 0 | 0 | 0
[12 empty] | 0 | [6 empty] | 0 | 0 | bar: FY2026
[12 empty] | 0 | [6 empty] | 0 | 0 | bar: FY2026
[12 empty] | 0 | [6 empty] | 0 | 0 | bar: FY2026
|  | FY2023: Total w/ IDC; FY2025: 0; FY2026: 0 | 0 | 0
~
~ | J. Outputs
~ | Output/Indicator | FY2021: Target Year; FY2022: Weight; FY2023: Rating; FY2024: Score; FY2025: Progress/Status |  |  | Action Plan if not On Track
Output 1:
0
0
0
Output 2:
0
0
0
0
0
Output 3:
0
0
0
Output 4:
0
0
0
Output 5:
0
0
0
| Output Rating | FY2022: 0%; FY2023: At Risk; FY2024: 0
~
~ | K. Safeguards
~ | Indicator | FY2021: Assessment Question; FY2024: Response / Comments |  | Rating | Action Plan if not On Track
A. Contract Awards
| 1. ENV: No works contracts are awarded before the EMP(s) cleared by ADB and any conditions of any national EIA/IEE clearance are incorporated into contract documents | FY2021: For any project outputs/ components with environmental impacts or risks, are there any works contracts that have been awarded by the borrower without EMP(s)* cleared by ADB and any conditions of any national EIA/IEE clearance incorporated into the bid and contract documents? |  | At Risk
| 2. IR: No civil works contracts are awarded before final, detailed engineering design-based RP(s) are cleared by ADB | FY2021: For any project outputs/ components, are there any civil works contracts that have been awarded by the borrower without ADB’s clearance of final, detailed-engineering design- based RP(s)? |  | At Risk
| 3. IP: No civil works contracts are awarded before final, detailed engineering design-based IPP(s) are cleared by ADB. | FY2021: For any project outputs/components, are there any civil works contracts that have been awarded by the borrower without ADB’s clearance of final, detailed-engineering design based IPP(s)?; FY2022: For any project outputs/ components, are there any civil works contracts that have been awarded by the borrower without ADB’s clearance of final, detailed-engineering design based IPP(s)? |  | At Risk
B. Project Execution: Instruments
| 4. ENV: Requisite national environment, health and safety clearances* and ADB environment safeguard clearances are obtained before commencement of applicable works. * Including permits, consents, licenses etc. | FY2021: For any project outputs/components with environmental impacts or risks, have the requisite national environment, health and safety clearances* and ADB environment safeguard clearances** been obtained before commencement of applicable works |  | At Risk
| 5. IR: No displacement occurs before all compensations are fully paid as confirmed by corresponding reporting.* *report definition as per OD | FY2021: For any project outputs/components, are there any civil works sites with involuntary resettlement impacts where access is granted to contractor(s) and economic and/or physical displacement occurs before compensations are fully paid to affected persons and other applicable assistance delivered in line with approved RP(s)? |  | At Risk
C. Project Execution: Grievances
| 6. The project has a functioning GRM and has no high-risk outstanding grievances related to implementation of safeguards. | FY2021: Does the project meet both criteria below: (a) has a functioning GRM; and (b) has NO Accountability Mechanism (CRP)-eligible complaint(s) on file? |  | At Risk
D. Project Execution: Safeguards Non-compliance
| 7. There are no outstanding non-compliances related to implementation of safeguards* *excluding non-compliances covered under Q1 through Q6 | FY2021: Does the project have any outstanding non-compliances* [can be notified by staff, external monitor, regulatory agencies, supervision consultants, borrower, or contractors]? *excluding non-compliances covered under Q1 through Q6 |  | At Risk
E. Project Execution: Monitoring
| 8. Scheduled monitoring reports* are submitted as per agreed schedule, commencing date loan effectiveness *Includes periodic FI implementation status reports | FY2021: Is the project up-to-date with the scheduled monitoring reports? |  | At Risk
| Safeguards Rating | [10 empty] | At Risk
~
~ | L. Gender Action Plan
~ | Status | FY2019: Issues; FY2022: Remarks
~
~ | M. Missions
~ | Date | FY2018: Type of Mission; FY2019: Aide Memoire; FY2020: BTOR; FY2021: Remarks
~
~ | N. Major Issues
~ | Item | FY2019: Mitigating Measure; FY2022: Status
~
~ | L. Other issues
~ | Item | FY2019: Mitigating Measure; FY2022: Status
Note on J130: Ma. Samantha Mendoza. Valdez: Contracts 0001-0005 under LN 3090 are under the same package with overal contract estimate of $5.8m
Note on J131: Ma. Samantha Mendoza. Valdez: Contracts 0001-0005 under LN 3090 are under the same package with overall contract estimate of $5.8m
Note on J132: Ma. Samantha Mendoza. Valdez: Contracts 0001-0005 under LN 3090 are under the same package with overall contract estimate of $5.8m
Note on J133: Ma. Samantha Mendoza. Valdez: Contracts 0001-0005 under LN 3090 are under the same package with overall contract estimate of $5.8m
Note on F176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: {Note: This includes project contracts outside ADB procurement process, and within the project’s scope}

## Field Definitions (hidden)
PPMS Field Definitions
Project Summary Section
Field | Field Type | Data Source | Formula | System Source
Title | Data |  |  | Operations Insights
Date | Data |  |  | Operations Insights
Project Name: | Data |  |  | Operations Insights
Project Number | Data |  |  | Operations Insights |  | `
Loan/Grant Number: | Data |  |  | Operations Insights
Executing/Implementing Agency: | Data |  |  | Operations Insights
ADB Administering Unit: | Data |  |  | Operations Insights
If TRJM, date of project transfer: | Data |  |  | Operations Insights
Sector/Subsector: | Data |  |  | Operations Insights
Project Officer: | Data |  |  | Operations Insights
Project Analyst: | Data |  |  | Operations Insights
Project Document Link: | Data
Project Handover Document Link: | Data
A. Loan/Grant Basic Data
Field | Field Type | Data Source | Formula | System Source
ADB Financing | Formula
Government Financing | Formula
Total ($ million equivalent) | Formula
Product | Data |  |  |  | Multiple Rows
Source | Data |  |  |  | Multiple Rows
Amount | Data |  |  |  | Multiple Rows
Approval | Data |  |  |  | Multiple Rows
Signing | Data |  |  |  | Multiple Rows
Effectivity | Data |  |  |  | Multiple Rows
Closing Original | Data |  |  |  | Multiple Rows
Closing Revised | Data |  |  |  | Multiple Rows
% Elapsed Time | Data |  |  |  | Multiple Rows
Environment Category | Data |  |  |  | Multiple Rows
Involuntary Resettlement Category | Data |  |  |  | Multiple Rows
Indigenous People's Category | Data |  |  |  | Multiple Rows
Gender Category | Data |  |  |  | Multiple Rows
B. Project Rating
Field | Field Type | Data Source | Formula | System Source
Parametrs | Data
Outputs | Data
Contract Awards (%) | Data
Disbursement (%) | Data
Financial Management | Data
Safeguards | Data
Overall Rating | Data
Reason | Data
Consecutive Overall Project Rating
Field | Field Type | Data Source | Formula | System Source
Year, Quarter 1 Label | Data
Year, Quarter 2 Label | Data
Year, Quarter 3 Label | Data
Year, Quarter 4 Label | Data
Year, Quarter (current) Label | Data
Year, Quarter 1 Value | Data
Year, Quarter 2 Value | Data
Year, Quarter 3 Value | Data
Year, Quarter 4 Value | Data
Year, Quarter (current) Value | Data
C. Contract Awards and Disbursements
Field | Field Type | Data Source | Formula | System Source
Quarter 1 Year Label | Data
Quarter 2 Year Label | Data
Quarter 3 Year Label | Data
Quarter 4 Year Label | Data
Year Total | Data
CA
Target-Total Cumulative | Formula
Target-Quarter 1 Year-eOps-Value | Data
Target-Quarter 1 Year-Committed-Value | Data
Target-Quarter 2 Year-eOps-Value | Data
Target-Quarter 2 Year-Committed-Value | Data
Target-Quarter 3 Year-eOps-Value | Data
Target-Quarter 3 Year-Committed-Value | Data
Target-Quarter 4 Year-eOps-Value | Data
Target-Quarter 4 Year-Committed-Value | Data
Target-Year Total-eOps-Value | Formula
Target-Year Total-Committed-Value | Formula
Achievement-Total Cumulative | Formula
Achievement-Quarter 1 Year | Data
Achievement-Quarter 2 Year | Data
Achievement-Quarter 3 Year | Data
Achievement-Quarter 4 Year | Data
Achievement-Year Total | Formula
(%)-Total Cumulative | Formula
(%)-Quarter 1 Year-eOps-Percentage | Formula
(%)-Quarter 1 Year-Committed-Percentage | Formula
(%)-Quarter 2 Year-eOps-Percentage | Formula
(%)-Quarter 2 Year-Committed-Percentage | Formula
(%)-Quarter 3 Year-eOps-Percentage | Formula
(%)-Quarter 3 Year-Committed-Percentage | Formula
(%)-Quarter 4 Year-eOps-Percentage | Formula
(%)-Quarter 4 Year-Committed-Percentage | Formula
(%)-Year Total-eOps-Percentage | Formula
(%)-Year Total-Committed-Percentage | Formula
DB
Target-Total Cumulative
Target-Quarter 1 Year-eOps-Value
Target-Quarter 1 Year-Committed-Value
Target-Quarter 2 Year-eOps-Value
Target-Quarter 2 Year-Committed-Value
Target-Quarter 3 Year-eOps-Value
Target-Quarter 3 Year-Committed-Value
Target-Quarter 4 Year-eOps-Value
Target-Quarter 4 Year-Committed-Value
Target-Year Total-eOps-Value
Target-Year Total-Committed-Value
Achievement-Total Cumulative
Achievement-Quarter 1 Year
Achievement-Quarter 2 Year
Achievement-Quarter 3 Year
Achievement-Quarter 4 Year
Achievement-Year Total
(%)-Total Cumulative | Formula
(%)-Quarter 1 Year-eOps-Percentage | Formula
(%)-Quarter 1 Year-Committed-Percentage | Formula
(%)-Quarter 2 Year-eOps-Percentage | Formula
(%)-Quarter 2 Year-Committed-Percentage | Formula
(%)-Quarter 3 Year-eOps-Percentage | Formula
(%)-Quarter 3 Year-Committed-Percentage | Formula
(%)-Quarter 4 Year-eOps-Percentage | Formula
(%)-Quarter 4 Year-Committed-Percentage | Formula
(%)-Year Total-eOps-Percentage | Formula
(%)-Year Total-Committed-Percentage | Formula
To be continued ….
D. Contract Awards and Disbursements (Annual Target vs. Actual CAD and CAD Ratios)
E. Output Delivery and Procurement
Output 1: Climate-resilient water supply and sanitation infrastructure rehabilitated and expanded
Output 2: Sustainable business model and institutional capacity developed
Project Management
F. Financial Management Compliance
G. Environmental Safeguards Compliance (fill in as applicable)
H. Social Safeguards Compliance (fill in as applicable)
I. Gender Action Plan
J. Missions
K. Major Issues
L. Other issues

## List (hidden)
| Countries |  | Project Rating | Procurement Selection Method | Contract Type | Rating | Weight | FM status | Mission Type |  | Safeguards Indicator 1 |  | Safeguards Indicator 2 |  | Safeguards Indicator 3 |  | Safeguards Indicator 4 |  | Safeguards Indicator 5 |  | Safeguards Indicator 6 |  | Safeguards Indicator 7 |  | Safeguards Indicator 8 | [5 empty] | Project Rating |  | Outputs (Technical) |  | Contract Award and Disbursement |  | Financial Management |  | Safeguards
AFG | Afghanistan | OT | On Track | ICB 1S1E | Works | Completed, target achieved by ≥85% | 1 | Not Required | Inception | 1 | Not Applicable | On Track | Not Applicable | On Track | Not Applicable | On Track | Not applicable and/or no clearances required. | On Track | No, all compensations/entitlements have been fully paid prior to displacement as confirmed by relevant ADB-cleared reports, for all project sites with involuntary resettlement impacts. | On Track | Yes, the project meets both criteria (functioning GRM and no CRP-eligible complaint(s) on file). | On Track | No | On Track | Not applicable. Cat C or an FI treated as C. | On Track | B. Financial Management Rating |  |  |  | Average | Overall Rating | Overall Weighted Score | Outputs Rating | Actual vs. Projected % Difference | CA&D Rating | FM Score | FM Rating | Responses | Safeguards Rating
ARM | Armenia | FA | For Attention | OCB 1S1E | Consulting Services | Completed, target underachieved by ≥16% | 0 | Deferred | Review | 2 | Unknown | For Attention | Unknown | For Attention | Unknown | For Attention | Not yet due, and/or no works requiring clearances were commenced prior to or during reporting period. | On Track | Not Applicable | On Track | Unknown or no functioning GRM. | For Attention | Unknown, due to any of the following: (1) external monitor not yet appointed, (2) no recent review mission fielded, (3) monitoring report to base decision on being overdue, (4) Other. | For Attention | Yes. Submitted, reporting up to date or is within a grace period of one month. | On Track | Indicator |  | Score | Action Plan if not On Track | >=90% | On Track (1.0) | >=85% | On Track (1.0) | >90% | On Track | >=75% | On Track | All On Track | On Track
AZE | Azerbaijan | AR | At Risk | ICB 1S2E | Non-Consulting Services | On track to meet target | 1 | Not yet Due | Special Project Admin | 3 | No, all contracts have been awarded and all include EMPs cleared by ADB and applicable conditions of national EIA/IEE clearance. | On Track | No, all contracts have been awarded after final RPs/DDRs were cleared. | On Track | No, all contracts have been awarded after final IPPs were cleared. | On Track | Yes, all clearances were obtained for all works commenced prior to or during reporting period. | On Track | Unknown | For Attention | No, the project has an Accountability Mechanism (CRP)-eligible complaint(s) but CAP implementation is on track for full compliance at end of CAP implementation period. | For Attention | Yes, no time-bound CAP agreed for non-compliance. | At Risk | Not yet submitted, reporting is overdue for 12 months or less. | For Attention | APFS |  | 50 | Will improve to OT by _______. {add action plan} | 65% to <90% | For Attention (0.7) | 70% to <85% | For Attention (0.7) | 75% to 90% | For Attention | 50% to 75% | For Attention | At least one response is For Attention and no At Risk | For Attention
GEO | Georgia |  |  | OCB 1S2E | Goods | On track to meet target, delayed | 0.7 | Yes | Project Completion | 4 | No, not all contracts are awarded. Contracts under bidding incl. EMPs cleared by ADB and applicable conditions of national EIA/IEE clearances. All awarded contracts included EMPs cleared by ADB and any conditions of applicable national EIA/IEE clearance. | On Track | No, not all contracts awarded, with final RPs/DDRs still pending for those contracts. Any awarded contracts meet the requirement of RPs/DDRs being cleared (no other options apply). | On Track | No, not all contracts awarded, with final IPPs still pending for those contracts. | On Track | Unknown | For Attention | No access is given to sites where compensations are ongoing or pending. | On Track | No, the project has an Accountability Mechanism (CRP)-eligible complaint(s) but CAP still in development or NOT on track for full compliance at end of CAP implementation period. | At Risk | Yes, still within time-bound CAP. | On Track | Not yet submitted or undisclosed, reporting and/or disclosure is overdue for more than 12 months | For Attention | AEFS |  | 25 |  | <65% | At Risk (0) | <70% | At Risk (0) | <75% | At Risk | <50% | At Risk | At least one response is At Risk or an assessment question unanswered | At Risk
KAZ | Kazakhstan |  |  | ICB 2S | EPC | On time, but potential risk of missing target | 0.7 | No | Consultation | 5 | No, not all contracts are awarded. Contracts under bidding do not contain EMPs cleared by ADB and/or any conditions of any national EIA/IEE [explain]. All awarded contracts included EMPs cleared by ADB and any conditions of any national EIA/IEE clearance. | For Attention | Yes, contract(s) have been awarded, with some RPs/DDRs pending to be finalized on a section-by-section basis within a contract package (and no other options apply). | For Attention | Yes, contracts have been awarded, with some IPPs pending to be finalized on a section-by-section basis. | For Attention | No. National EIA/IEE clearance*** is obtained for project output/component but other clearances missing; time bound corrective action plan is in place to obtain. Plan is 3 months or less overdue. | For Attention | Yes | At Risk |  |  | Yes, implementation of time-bound CAP actions overdue for 3 months or less. | For Attention |  |  | Compliance with Financial Covenants |  | 25 | [5 empty] | Ex. Actual cumulative CA = 10
KGZ | Kyrgyz Republic |  |  | OCB 2S |  | On time, will underachieve target | 0 |  | Midterm Review | 6 | Yes, awarded contract is turnkey/DBO/EPC** but it includes an outline design-based EMP cleared by ADB and any conditions of any national EIA/IEE clearance. | On Track | Yes, a contract is turnkey/DBO/EPC, and it includes requirements for civil works to be conditional upon clearance of final RPs/DDRs (no other options apply). | On Track | Yes, a contract turnkey/DBO/EPC but it includes requirements for civil works to be conditional upon clearance of final IPPs. | On Track | No. National EIA/IEE clearance*** is obtained for project output/component but other clearances missing; no time bound corrective action plan in place to obtain them, or corrective action is more than 3 months overdue. | At Risk | Yes, corrective action has been taken, and all compensations are now paid as verified through relevant compliance reports cleared by ADB. | On Track |  |  | Yes, implementation of time-bound CAP actions overdue for more than 3 months. | At Risk |  |  | Financial Management Rating | Potential Problem | [6 empty] | Projected CA starting at effectiveness = 12.5
PAK | Pakistan |  |  | Shopping |  | Delayed and potential risk of missing target | 0.7 |  |  | 7 | Yes, awarded contract is turnkey/DBO/EPC** but it excludes an outline design-based EMP cleared by ADB and/or any conditions of any national EIA/IEE clearance. | At Risk | Yes, a contract is turnkey/DBO/EPC, but it excludes requirements for civil works to be conditional upon clearance of final RPs. | At Risk | Yes, a contract turnkey/DBO/EPC but it excludes requirements for civil works to be conditional upon clearance of final IPPs. | At Risk | No. National EIA/IEE clearance*** is missing for any works commenced prior to or during reporting period | At Risk | [16 empty] | % difference = 10/12.5 = 80%
TAJ | Tajikistan |  |  | RFQ |  | Not started, delayed by ≤ 6 months | 0.7 |  |  | 8 | Yes, a standard contract was awarded without including EMP cleared by ADB and/or any conditions of any national EIA/IEE clearance. | At Risk | Yes, a standard contract was awarded without ADB’s prior approval of final RP/DDR. | At Risk | Yes, a standard contract was awarded without ADB’s prior approval of final IPP. | At Risk | Corrective action has been taken, and all clearances for all works commenced prior to or during reporting period have now been obtained. | On Track
TKM | Turkmenistan |  |  | Direct Contracting |  | Not started, delayed by ≥ 7 months | 0 |  |  | 9 | Yes, corrective action (by contract variation) has been taken following any contract award to incorporate EMP cleared by ADB and/or any conditions of any national EIA/IEE clearance into contract. | On Track | Yes, corrective action has been taken, and detailed engineering design-based RPs were updated/prepared and cleared after contract award. | On Track | Yes, corrective action has been taken, and IPPs were updated/prepared and cleared after contract award. | On Track
UZB | Uzbekistan |  |  | LCB |  | Cancelled | 0
REG | Regional |  |  | LIB |  | Not due to start | 1
PRC | PRC |  |  | e-Auction
MON | Mongolia |  |  | Force Account
QCBS
QBS
CQS
FBS
LCS
ICS
Others
| ENV/IR/IP |  | Gender
| A |  | Gender Equity Theme
| B |  | Effective Gender Mainstreaming
| C |  | Some Gender Benefits
| FI |  | No Gender Elements
=IF(ISBLANK(F100),0,(VLOOKUP(G100,'List'!I13!$G$2:$H$12,2,FALSE))*F100)